## Read Me
AI Resume Builder – QA Test Documentation
Prepared by | Aditi
Test cycle | QA Test Cycle 1
Application | AI Resume Builder
Frontend | Vercel deployment
Backend | Render deployment
Database | MongoDB Atlas
API tool | Postman
Testing date | 7 October 2026
Testing covered | Manual UI, registration, API, database validation, resume sharing, persistence, authentication and defect reporting
Automation status | 3 Playwright tests (AUTO-001 to AUTO-003) were run on 8 Oct 2026: 3 passed. They use the real frontend with the backend API mocked, and are reported on the Automation sheet, separate from the 77 executed tests.
Important note | All results in this workbook are based on tests actually executed and observed. No assumed or unexecuted results are included.
Status meaning | PASS = expected behavior observed; FAIL = actual behavior differed from expected result.

## Test Cases
Test Case ID | Module | Test Scenario | Steps / Test Data | Expected Result | Actual Result | Status | Defect ID
TC-001 | Login | Blank email and password | Leave both fields blank and submit | Required validation should appear | Required-field validation appeared | PASS
TC-002 | Login | Invalid email format | Enter aditi123 as email | Invalid email should be rejected | Validation indicated email must include @ | PASS
TC-003 | Login | Unregistered email | Enter unregistered email with password | Login should be rejected | Invalid email or password | PASS
TC-004 | Login | Correct email with wrong password | Enter valid email and incorrect password | Login should be rejected | Invalid email or password | PASS
TC-005 | Login | Valid credentials | Enter valid registered credentials | Dashboard should open | Dashboard opened and greeting displayed | PASS
TC-006 | Dashboard | Dashboard loading | Login and open dashboard | Dashboard should load correctly | Dashboard and resume options loaded | PASS
TC-007 | Resume Creation | Blank title | Leave title blank and continue | Title should be required | Required validation appeared | PASS
TC-008 | Resume Creation | Valid title | Enter Aditi QA Resume | Resume editor should open | Resume editor opened | PASS
TC-009 | Personal Info | Required email blank | Leave email blank and continue | Required email should block progression | User was allowed to continue | FAIL | BUG-001
TC-010 | Personal Info | Valid email | Enter valid email | Email should be accepted | Accepted and progression allowed | PASS
TC-011 | Personal Info | Invalid email | Enter aditi123 | Invalid email should be rejected | Invalid email was accepted | FAIL | BUG-002
TC-012 | Professional Summary | Blank summary | Continue without summary | Configured optional/required behavior should apply | User was allowed to continue; no blocking validation observed | PASS
TC-013 | Professional Summary | Valid summary | Enter valid summary and continue | Summary should be accepted | Accepted and progressed | PASS
TC-014 | Experience | Add experience | Enter experience details and add/save | Experience should be added | Experience added successfully | PASS
TC-015 | Experience | AI enhance job description | Enter job description and use AI enhancement | One clean enhanced description should be returned | Multiple alternatives, explanations and placeholders returned | FAIL | BUG-006
TC-016 | Experience | Continue to Education | Proceed after experience | Education should open | Education opened | PASS
TC-017 | Education | Empty education | Leave education empty and continue | Progression should work if optional | Progressed to Projects | PASS
TC-018 | Projects | Empty projects | Leave projects empty and continue | Progression should work if optional | Progressed to Skills | PASS
TC-019 | Skills | Empty skills | Leave skills empty and continue | Progression should work if optional | Progressed to resume output | PASS
TC-020 | Resume Output | Download resume | Use Download option | Resume should download | Resume downloaded | PASS
TC-021 | Public Sharing | Make resume public | Enable public toggle and open link | Public resume should be accessible | Public link accessible | PASS
TC-022 | Public Sharing | Private resume access | Disable public access and open link | Private resume should not be accessible | Private link inaccessible | PASS
TC-023 | Public Sharing | Restore public access | Enable public access again | Public link should become accessible | Public link accessible again | PASS
TC-024 | Public Sharing | Public name display | Open public resume after saving name | Saved name should display | Displayed default 'Your Name' | FAIL | BUG-003
TC-025 | Public Sharing | Verify other public fields | Check email, summary, experience, education, projects, skills | Saved fields should display | Other verified fields displayed correctly | PASS
TC-026 | Profile Photo | Upload profile photo | Select a valid profile image | Image should upload | Failed with imagekit.upload is not an function | FAIL | BUG-004
TC-027 | Persistence | Refresh after editing | Make changes and refresh | Saved changes should remain | Changes remained except updated name | FAIL | BUG-005
TC-028 | Persistence | Logout and login again | Logout then login | Existing resume data should remain | Resume data remained | PASS
TC-029 | Personal Info | Valid name | Enter valid name | Name should be accepted | Accepted | PASS
TC-030 | Personal Info | Very long name | Enter very long name | Input should be handled | Accepted/handled | PASS
TC-031 | Personal Info | Special characters in name | Enter name with special characters | Input should be handled | No issue observed | PASS
TC-032 | Personal Info | Name persistence | Change name and refresh | Updated name should persist | Updated name did not persist | FAIL | BUG-005
TC-033 | Experience | Add second experience | Add another experience | Second experience should be added | Added successfully | PASS
TC-034 | Experience | Edit experience | Edit existing experience | Changes should save | Edited successfully | PASS
TC-035 | Experience | Delete experience | Delete existing experience | Experience should be removed | Deleted successfully | PASS
TC-036 | Experience | Experience persistence | Refresh after saving experience | Experience should remain | Experience remained | PASS
TC-037 | Education | Add/edit/delete education | Perform add, edit and delete | Changes should work | Operations worked | PASS
TC-038 | Projects | Add/edit/delete projects | Perform add, edit and delete | Changes should work | Operations worked | PASS
TC-039 | Skills | Add multiple skills | Add multiple skills | Skills should be added | Added successfully | PASS
TC-040 | Skills | Remove skill | Remove existing skill | Skill should be removed | Removed successfully | PASS
TC-041 | Skills | Skills persistence | Refresh after saving skills | Skills should remain | Skills remained | PASS
TC-042 | Authentication | Logout | Click logout | User should be logged out | Returned to Home/Landing | PASS
TC-043 | Authentication | Dashboard after logout | Attempt dashboard while logged out | Authentication should be required | Login/signup required | PASS
TC-044 | Authentication | Login after logout | Login again with valid credentials | Dashboard should open | Dashboard opened | PASS
TC-045 | Resume Deletion | Delete resume | Delete and confirm | Resume should be deleted | Deleted successfully | PASS
TC-046 | Resume Deletion | Old public link after deletion | Open deleted resume public URL | Deleted resume should not be accessible | Resume not found | PASS
TC-047 | Resume Creation | Create after deletion | Create QA Test Resume 2 | Editor should open | Editor opened normally | PASS
R-01 | Registration | Blank registration fields | Submit with required fields blank | Required validation should appear | Please fill out this field appeared | PASS
R-02 | Registration | Invalid registration email | Enter invalid email | Invalid email should be rejected | Validation shown | PASS
R-03 | Registration | Existing email | Register with existing email | Duplicate should be rejected | User already exists message shown | PASS
R-04 | Registration | Valid new registration | Register valid new account | Account should be created | Account created successfully | PASS
API-001 | Users | Register valid user | POST /api/users/register | 201 and user/token | User created successfully; no password returned | PASS
API-002 | Users | Login valid user | POST /api/users/login | 200 and token/user | Login successful; no password returned | PASS
API-003 | Users | Wrong password | POST login with wrong password | Request rejected | Invalid email or password | PASS
API-004 | Users | Unknown email | POST login with unknown email | Request rejected | Invalid email or password | PASS
API-005 | Users | Missing email | POST register without email | Request rejected | Missing required fields | PASS
API-006 | Users | Duplicate email | POST register with existing email | Request rejected | User Already exists | PASS
API-007 | Users | User data with valid token | GET /api/users/data with valid token | User data returned | Matching user returned; no password | PASS
API-008 | Auth | User data without token | GET /api/users/data without Authorization | 401 expected | Unauthorized. No token provided. | PASS
API-009 | Auth | User data with fake token | GET /api/users/data with invalid token | 401 expected | Unauthorized. Invalid token. | PASS
API-010 | Resumes | Get user resumes | GET /api/users/resumes | Resume list returned | Valid resume list returned | PASS
API-011 | Resumes | Create resume | POST /api/resumes/create | Resume created | Resume created successfully with ID | PASS
API-012 | Resumes | List resumes | GET /api/resumes/ | Created resume returned | API Test Resume returned | PASS
API-013 | Resumes | Get resume by ID | GET /api/resumes/get/:resumeId | Specific resume returned | Correct resume returned | PASS
API-014 | Resumes | Update resume | PUT /api/resumes/update/:resumeId | Resume updated | Update successful; title changed | PASS
API-015 | Resumes | Private public endpoint | GET public/:resumeId while private | Private resume rejected | Resume not found | PASS
API-016 | Resumes | Make resume public | PUT update public=true | Public flag updated | Public became true | PASS
API-017 | Resumes | Get public resume | GET public/:resumeId without auth | Public resume returned | Full public resume returned | PASS
API-018 | AI | Enhance professional summary | POST /api/ai/enhance-pro-sum | Enhanced content returned | EnhancedContent returned | PASS
API-019 | AI | Enhance job description | POST /api/ai/enhance-job-desc | One clean enhancement expected | Multiple options/explanations/placeholders; initial attempts timed out | FAIL | BUG-006, BUG-007
API-020 | AI | Upload existing resume | POST /api/ai/upload-resume | Resume ID returned | Resume ID returned | PASS
API-021 | Resumes | Delete resume | DELETE /api/resumes/delete/:resumeId | Resume deleted | Resume deleted successfully | PASS
DB-001 | Database | Verify user record | Check users collection | Correct user record with protected password storage | User found; password stored as bcrypt hash | PASS
DB-002 | Database | Verify deleted resume | Check deleted resume ID | Deleted resume absent | Deleted resume not found | PASS
DB-003 | Database | Verify uploaded resume | Check uploaded resume ID | Uploaded data persisted | Expected resume document found | PASS
DB-004 | Database | Verify user-resume relationship | Compare userId values | IDs should match | userId matched test user | PASS
DB-005 | Database | API-to-DB consistency | Compare API result with MongoDB | Persisted data should match | Consistency confirmed | PASS

## Summary
AI Resume Builder – QA Test Sheet
Prepared by | Aditi
Purpose | Detailed record of executed QA tests
Scope | Manual UI, Registration, API and Database testing
Automation | 3 Playwright UI tests executed separately (see Automation sheet); not included in the 77 below
Category | Executed | Pass | Fail
Manual / UI / Registration | 51 | 44 | 7
API | 21 | 20 | 1
Database | 5 | 5 | 0
TOTAL | 77 | 69 | 8
Note | Counts reflect only tests actually executed and observed. No unexecuted automation tests are presented as completed.
Documented defects | 7
Regression status | Not a post-fix regression cycle; critical-flow recheck/follow-up is separate.
Automation (separate)
Category | Executed | Pass | Fail
Playwright UI (mocked API) | 3 | 3 | 0

## Defects
Bug ID | Module | Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | Test Case Ref | Date Reported | Environment
BUG-001 | Personal Info | Required email allows progression when empty | Medium | Medium | 1. Log in and create a resume. 2. Open Personal Info. 3. Leave Email blank. 4. Click Continue. | Required email should block progression | User could continue with email blank | Open / Reported | TC-009 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-002 | Personal Info | Invalid email format accepted | Medium | Medium | 1. Open Personal Info in the resume editor. 2. Enter aditi123 in Email. 3. Click Continue. | Invalid email should be rejected | Invalid email such as aditi123 was accepted | Open / Reported | TC-011 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-003 | Public Resume Sharing | Public resume displays default name | High | High | 1. Save a name in Personal Info. 2. Enable the public toggle. 3. Open the public resume link. | Saved name should appear publicly | Public page displayed 'Your Name' | Open / Reported | TC-024 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-004 | Profile Photo | Profile photo upload fails | High | High | 1. Open Personal Info. 2. Select a valid profile image. 3. Upload it. | Valid photo should upload | Upload failed with 'imagekit.upload is not an function' | Open / Reported | TC-026 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-005 | Personal Info / Persistence | Updated name does not persist after refresh | High | High | 1. Change the name in Personal Info. 2. Save. 3. Refresh the page. | Updated name should persist | Name did not persist while other changes remained | Open / Reported | TC-027, TC-032 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-006 | AI API | Job-description enhancement returns mixed response instead of one clean result | Medium | Medium | 1. In Experience, enter a job description and use AI enhancement. (API: POST /api/ai/enhance-job-desc) | One clean enhanced description should be returned | Multiple alternatives, explanations and placeholders returned | Open / Reported | TC-015, API-019 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas
BUG-007 | AI API | Initial job-description enhancement API attempts timed out | Low | Low | 1. Send POST /api/ai/enhance-job-desc. 2. Observe the first attempts. | API should respond within a reasonable time | Initial attempts timed out; a later attempt returned a response. Root cause not established. | Open / Reported | API-019 | 7 Oct 2026 | Frontend: Vercel; Backend: Render; DB: MongoDB Atlas

## Automation
Test ID | Scenario | Steps | Expected Result | Actual Result | Status | Tool / Browser | Run Date | Scope
AUTO-001 | Login with valid credentials | 1. Open /app 2. Enter valid email and password 3. Click Login | Success message shown; dashboard with Create Resume and Logout opens | Matched expected result | PASS | Playwright 1.56.0 / Chromium | 8 Oct 2026 | Real frontend code run locally; backend API mocked (UI only, not live API/DB)
AUTO-002 | Login with wrong password | 1. Open /app 2. Enter email and wrong password 3. Click Login | 'Invalid email or password' shown; user stays on login; no Logout button | Matched expected result | PASS | Playwright 1.56.0 / Chromium | 8 Oct 2026 | Real frontend code run locally; backend API mocked (UI only, not live API/DB)
AUTO-003 | Create resume with title | 1. Open dashboard (logged in) 2. Click Create Resume 3. Enter title Aditi QA Resume 4. Submit | Resume builder opens at /app/builder/<id> | Matched expected result | PASS | Playwright 1.56.0 / Chromium | 8 Oct 2026 | Real frontend code run locally; backend API mocked (UI only, not live API/DB)